## A3 Form
A3 | [5 empty] | Date: | 2026-07-29 10:44
| SIC: | Location: |  |  | Sponsor: |  | Kaizen #:
Team Name:
Step 1: Theme | Team Leader: |  |  |  | Step 6: Implementation
Team Members:
Sensei:
Step 2: Boundaries/Scope | Step 4: SMART Targets
|  | Current | Target | Actual
Step 3: Grasp the Situation/Current State
VOC:
Symptoms:
Step 7: Lessons Learned
Step 5: Action Plan
Impact: | Action | Person | Due Date | % Comp
Step 8: Parking Lot
Potential Root Causes:
Step 9: Value of Improvements

## Instructions
Instructions for completing the A3
Key point #1 - the A3 process is not simply filling in the boxes on a form. The team-based problem definition, discovery, root cause identification and problem solving process is the key to "A3 Thinking!"
Key Point #2 - an effective A3 clearly demonstrates how he suggested improvements and countermeasures will address the current problem
Document a complete summary of the project on the one-page A3 form, so that a person can quickly review it and understand the project objectives and status at a glance. Use the worksheet tabs to capture supporting details.
Periodically post the newest version of the A3 on the communications board in the work area of the process owner (team leader)
Team name
Short-name for the project
1 Theme
Briefly describe the project in such a way that it clearly communicates the essence of what you are trying to address. State the theme as a problem to be solved and not a predetermined solution.
2 Boundaries
What is in and out of scope, who is involved, what types of events/transactions, what time boundaries?
Might software development or other systems intervention be required, or are we first going to improve the process and later determine if system interventions are needed? The latter approach is usually preferred.
Be sure to also state what is NOT included in scope
Be specific, it is very easy to make invalid assumptions that will get you into trouble later
3 Grasp the Situation/Current State
Begin with the Voice of the Customer - who is the customer (internal or external)? How do they define value/what specifically do they want? How would you measure this? Do you have a baseline?
Follow the suggested process for a complete Box 3 analysis:
1. Define current state using maps, narratives, artifacts, etc.
2. Identify problems (pain points, gaps)
3. Root cause analysis on key problems
4. Identify potential countermeasures to fix root causes
5. Impact/Ease analysis to prioritize these countermeasures
6. Determine the changes you will implement
7. Draw future state to reflect what the changes will look like
8. Then define your targets based on this future state and develop your action plan
Use diagrams, photos, bullet points, narrative - whatever is appropriate to describe the current situation
Identify problems and their impact on Quality, Cost, Time (delivery and process) and Morale
Do not move on to the next step until you have clearly identified the ROOT CAUSES of these problems! - Remember to use the "5 Whys"
4 SMART Targets
Measure must address the root cause and action plan
SMART = Specific, Measurable, Actionable, Realistic, Timely
5 Action Plan
Task list area
Use the A3 form area for milestones and/or limited number of tasks
Use the Kaizen newspaper tab if there are a large number of tasks
6 Implementation
While you are developing a solution this area is helpful to store a description of your desired future state
Once you implement, this area is used to store a description of the final solution - the previous definition of the desired future state may be archived in the implementation tab area
7 Lessons learned
Provide information on what worked, what didn’t, and any other key learning
What was learned that could be applied to other projects?
Make notes during the project, and be sure to debrief after the project is complete
8 Parking lot
Capture issues, problems and ideas as they arise. Also capture out-of-scope items that should be addressed separately. If these are the domain of another group that is not part of this project, this may be an indication that they should be involved (or at least communicated with)
If there is a company-wide database to track these issues, be sure to enter them there as well
9 Cost savings and calculations
Make sure that these align with strategic goals, balanced scorecard, and other specific measures
Use quantitative data whenever possible, document the assumptions and calculations used
Not all savings are "hard" savings, make an effort to document and quantify soft savings that add value to the customer In terms of quality, delivery, and cost)

## VOC
Voice of the Customer
Suggest you complete each column before moving to the next one
How well do we understand?
Customer/Partner | Internal/External | H/M/L | What are their requirements? | Specifically how do we measure them?

## Current state
Current State - Save additional details and supporting information here

## SMART Targets
SMART Targets - Save additional details and supporting information here

## Action Plan
# | Problem / Issue / Opportunity | Action Needed | Owner | Creation Date | Date/Time Due | % Complete

## Implementation
Implementation - Save additional details and supporting information here

## Lessons learned
Lessons Learned - Save additional details and supporting information here

## Parking Lot
Parking Lot - Save additional details and supporting information here

## Value of Improvements
Value of Improvements and Calculations - Save additional details and supporting information here